## Sheet1
|  |  | 2014-10-20 | 2014-10-27 | 2014-11-03 | 2014-11-10 | 2014-11-17 | 2014-11-24 | 2014-12-01 | 2014-12-08 | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-05 | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-02-02 | 2015-02-09 | 2015-02-16 | 2015-02-23 | 2015-03-02 | 2015-03-09 | 2015-03-16 | 2015-03-23 | 2015-03-30 | 2015-04-06 | 2015-04-13
| end on the week shown inclusively |  | 2014-10-20: weeks starting form the beginning of the project
Task | Start Date | End date | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | week 13 | week 14 | week 15 | week 16 | week 17 | week 18 | week 19 | week 20 | week 21 | week 22 | week 23 | week 24 | week 25 | week 26
Research relevant APIs | 2014-10-20 | 2014-11-10 | bar: weeks starting form the beginning of the project week 1 to weeks starting form the beginning of the project week 4
Create interface | 2014-11-17 | 2014-12-15 | bar: weeks starting form the beginning of the project week 5 to weeks starting form the beginning of the project week 9
Christmas | 2014-12-22 | 2014-12-29 | bar: weeks starting form the beginning of the project week 10 to weeks starting form the beginning of the project week 11
Continue creating interface | 2015-01-05 | 2015-01-26 | bar: weeks starting form the beginning of the project week 12 to weeks starting form the beginning of the project week 15
contingency | 2015-02-02 | 2015-02-02 | bar: weeks starting form the beginning of the project week 16
Create custom Scratch blocks | 2015-02-09 | 2015-02-16 | bar: weeks starting form the beginning of the project week 17 to weeks starting form the beginning of the project week 18
Create materials for focus group | 2015-02-23 | 2015-03-02 | bar: weeks starting form the beginning of the project week 19 to weeks starting form the beginning of the project week 20
Organise a focus group session | 2015-02-23 | 2015-03-09 | bar: weeks starting form the beginning of the project week 19 to weeks starting form the beginning of the project week 21
Run a focus group session | 2015-03-09 | 2015-03-09 | bar: weeks starting form the beginning of the project week 21
Evaluate the results of the test | 2015-03-16 | 2015-03-30 | bar: weeks starting form the beginning of the project week 22 to weeks starting form the beginning of the project week 24
Contingency | 2015-04-06 | 2015-04-06 | bar: weeks starting form the beginning of the project week 25
Print and submit | 2015-04-13 | 2015-04-13 | bar: weeks starting form the beginning of the project week 26
Literature review | 2014-12-15 | 2015-04-13 | bar: weeks starting form the beginning of the project week 9 to weeks starting form the beginning of the project week 26
Write up | 2014-12-15 | 2015-04-13 | bar: weeks starting form the beginning of the project week 9 to weeks starting form the beginning of the project week 26